## Sheet1
Tasks
Identifying SDLC to use
Planning | Prerequisite of the SDLC chosen
Create Database | Dependent on the data that exists
Create data analysis GUI | Prerequisite of the database
Analyzing sorting data | Prerequisite of the database
Testing | Prerequisite of the GUI
COSTING
Laptop - £500
Mouse - £20
Microsoft 365 F3 - £7/month
BoldLeads - £400-£620/month
Rationale:
The project is significant as it will allow the the company to work from a centralized system.
It will make data analysis easier and faster.
It will allow further integratinos to be made in the future.
The current issue would be